| Project Name: | WARPIT | Project Manager: | Julie Parkinson |
| --- | --- | --- | --- |
| Project Sponsor/ Executive | Lee Jackson | Proposed Start Date: | 28th November 2012 |
|  |  | Proposed End Date: | On-going |

| - Background: |  |  |  |
| --- | --- | --- | --- |
| About WARPIT: WARPIT is an easy to use online portal which provides a platform for organisations to redistribute (give, loan or share) resources legally and conveniently within the organisation and beyond, within other organisations. The tool demonstrates significant savings on purchasing and waste disposal costs, as well as avoiding landfill and carbon emissions. There are two scenarios which mean as an organisation our resources are often wasted. Due to limited communications and space and time pressures, we often have to dispose of surplus resources because a new owner cannot be found quickly and easily. Furthermore it is human nature to hoard items that might be needed later – this leads to inefficient space and the stored unused resources are not in use and become obsolete. Organisations using WARPIT range from Local Authorities, Central Government, NHS, Universities, Colleges and Schools, SME’s and groups with charitable purposes. Northumberland County Council’s Introduction to WARPIT: Following a presentation to the Sustainable Procurement Working Group by Daniel O’Connor of WARPIT (Waste Action Reuse Portal), a further presentation was arranged on 17th August to generate discussion and gain approval of this portal for Northumberland County Council. Heads of Service and Senior Officers across service areas were invited to attend, but with only 5 officers in attendance, it was agreed that action should be taken to implement this system as it is an excellent opportunity for the authority to act in a sustainable manner. A quick analysis of data prior to the meeting on 17th August showed that as an authority we had spent £55,025.10 on furniture with our contracted supplier from April 2011 to June 2011. The idea of this portal will not only ensure we act in a sustainable manner, but to encourage growth and development with organisations in Northumberland as part of the process; and to ensure that as an authority we are making efficient use of resources with procedures in place for unwanted items. The cost of this portal is £2,000 plus VAT per annum and includes all NCC owned and managed estates including schools, with 24/7 customer support. Phase 2- Implementation Plan; To date the Councils implementation of WARPit has been a resounding success with over £63,000 cost avoidance and 42,000 tonnes of carbon saved. However not all items have been claimed which has led to the main storage area (Old Fire Station at County Hall, Morpeth) becoming overly full The aim of phase 2 is to allow NCC staff members to claim items on a personal basis predominantly for use in the home. A £5 contribution to go towards covering the portals annual subscription costs will be required. This will be paid in cash by the claimant and receipted. Objectives: The aim is to ensure that the maximum possible amounts of resources are being re-used, the reasons for this are listed below; - Avoidance of waste disposal (impact on costs and landfill) - Avoidance costs of purchasing new resources which could be free - Reduction in carbon emissions generally associated with purchasing - Ensures management of recycling and refurbishment of resources across authority - Social benefits for local Third Sector organisations joining the portal at no cost - Encourages business growth and development – using local organisations as part of refurbishment process - Encourages business growth and development – using local organisations when setting framework for delivery arrangements - Ensuring best value for money and efficiency savings All options, risks and issues are to be identified as part of the project. WARPit works by having its users grouped into 3 priority levels. To maximise value to the Council it is important to try and reuse items within the organisation. Internal subscribers are known as Priority 1 subscribers. The more internal subscribers, the more chance that the items will be reused within the organisation and save money on purchasing new equipment. Priority 2 and priority 3 are occupied by collaborating organisations. Priority 2 is made up of reciprocal resource sharing networks e.g. Durham County Council. Organisations can link up (‘friend’ each other) locally, nationally and internationally to share resources. Priority 3 organisations are usually made up of community groups, charities or SMEs, these organisations do not reciprocally share but may want to transfer items. On NCC’s WARPit portal resources become available to priority 2 and priority 3 organisations a pre-determined number of days before the resource ‘expires’. As shown in the diagram below, Phase 2 will allow staff members to claim resources when they become available to priority 2 and 3 users. Normal WARPit model; (Time available to claim) Priority 1 (NCC) Priority 2 e.g. Durham County Council Priority 3 e.g. charities Phase 2 NCC model; (Time available to claim) Priority 1 (NCC) Priority 3 NCC Staff Priority 2 Benefits: - Cost benefits - Carbon reduction - Enhance relations with VCS - Reduced strain on storage facilities - Less wasted resource - Recoup of WARPit subscription costs KPI data generated by the WARPit portal can be used to assess the impact of implementing phase 2. |  |  |  |
| - Options Appraisal: |  |  |  |
| Option 1: Do nothing Strengths; Weaknesses; Opportunities; Threats. No change to current practises; Build-up of unwanted items/furniture (and associated disposal costs); Focus time and effort on other initiatives; Lowered efficiencies and savings. No further resource required. Option 2: Implement Phase 2 Strengths; Weaknesses; Opportunities; Threats. Recoup of subscription costs; Resources to implement and manage; Provide low cost furniture and other resources to staff; System not utilised to full potential. Efficiency savings; Good staff relations opportunity. Sustainable solution. Process to dispose unwanted (by Council) items/furniture. Option1 - Do nothing: This option must be discounted because it contradicts the Councils sustainable objectives and does nothing to improve current reuse rates. Option 2 – Implementing Phase 2 Recommend this option because for low resource use significant benefits could be achieved. |
| - Outcomes/Benefits expected, how they will be measured and when: |  |  |  |
| Outcomes; How; When. - Cashable savings; - Reduced number of items to landfill - £5 contributions to be put towards recouping the procurement departments subscription fee for WARPit; From December 2012. - Process efficiencies; - Reducing number of unwanted items going to landfill – improvement of waste management arrangements; From December 2012. |
| - Scope: (noting any exclusions) |  |  |  |
| The scope to manage this phase of the portal will be within Procurement. |  |  |  |
| - Cost: |  |  |  |
| Summary of Financial implications: (Avoidance of waste disposal/waste transportation costs) Have there been collections- ask JP/PS |  |  |  |
| - Timescales: |  |  |  |
| Implementation can be completed by 12th December 2012 subject to communications on NCC Intranet and ‘Staff Room’ e-newsletter and approval from audit, trading standards and legal personnel. Enquiries regarding these communications have been made and timely completion for a ‘going live’ date of 12/12/12 seems feasible. - Changes to customised messages; 12/12/12 - Staff Room Communication; 12/12/12 - WARPit Intranet page amended; 12/12/12 |  |  |  |
| - Initial Risks: |  |  |  |
| Area; Measure; Comments. Internal resource not able to meet delivery requirements; Monitor response level prior to ‘going live’ date; Josh Brown able to assist. Safety concerns regarding staff members moving items of furniture between storage and vehicles; Create new risk assessment form including contact info for Revive- a local social enterprise providing transport at reasonable prices; New risk assessment form can be found in S:\Commercial & Procurement Services\CP Tenders & Projects\CP72 WARPIT. Liability; - Terms and conditions clearly state ownership and responsibility is transferred on collection of goods. - Signed risk assessment will have to be collected before goods can be passed on - Receipt will outline transfer of ownership; Receipt wording can be viewed in S:\Commercial & Procurement Services\CP Tenders & Projects\CP72 WARPIT. |
| 8. Amendment History: |  |  |  |
| Version | Date | Author | Reason |
| 0.1 | 03/12/2012 | Gordon Pearson | Approval required for implementation |