North Tyneside Council

WARPit PROGRESS REPORT

(March to May 2013)

- Introduction: WARPit

WARPit (Waste, Action Reuse Portal) is a free online resource which makes easier for different parts of an organization to advertise things they no longer need or want. Its aims to save waste disposal, improve space efficiency and avoid unnecessary procurement. Staffs from across the organisation are encouraged to list any unwanted or underused items for others to have, shared or borrow. More details can be found at: www.warp-it.co.uk

- WARPit at North Tyneside Council

The WARPit progress update for North Tyneside Council (NTC) can be viewed at: www.warp-it.co.uk/ntc . There are total 164 members associated with WARPit at NTC as noted on 30 May 2013. (Annex-I: WARPit users’ report at NTC)

- Role of Intern

Suman Dhun Shrestha, an MSc student from Northumbria University joined the Environmental Sustainability team on a three-month internship, specifically to promote and take over reins of the WARPit. Suman was on hand to help with any WARPit related queries, while also providing support in preparing inventories and registering users and equipment in the scheme.

- Communications Efforts

Since March 2013, communications have been made on WARPit to alert all service areas of the council to take part in WARPit system. Specifically following efforts were made:

- Emails circulated to all procurement users and service areas of the council by Paul Nelson.

- Article on WARPit published in March issue of ‘Teamwork’, a monthly staff newsletter. (Annex-II)

- Letters introducing WARPit and requesting participation was send to all schools through Ian Betham, (Annex-III)

- WARPit progress news in weekly ‘Team News’ of 7 May 2013. (Annex-IV)

- WARPit progress news in monthly newsletter ‘Teamwork’ of May 2013. (Annex-V)

- New members added

Between March to May 2013, 35 new members were added to North Tyneside Council WARPit system.

- Preparation of inventory

Fig-1: A glimpse of Killingworth site

Inventories were was prepared mainly from three sites: (i) Killingworth block of NTC, (ii) Whitley Bay Library and (iii) North Shields Library. Field visits were made to Killingsworth, Whitley Bay library and North Shields respectively on 21st March, 28th March and 29 May 2013. After finalizing the list of inventory, appropriate items were uploaded in WARPit system.

Between March to May, 252 items of approx. 20 different varieties were categorized and uploaded in the WARPit system. (Annex- VI: Report of items in WARPit)

- Items diverted

The items diverted after March 2013 are mainly: Display, Bookcase, Wooden tables, Operator Chairs (operators and upright stacking chair), Storage containers, Office desk, Book cases, Drawer and Information Shelves. Most of the items diverted were from Killingworth block and Whitley Bay library. 64 items were diverted

- Challenges/ Issues

During the project period few challenges and issues are identified which are as follows:

8.1’Claimed items’ tab

It was realized little confusion with the available item when photo was not available after the items were claimed. Especially when there different variety of items under common WARPit automated headings.

Action taken: Issue reported to WARPit administration.

8.2 Request and claims from other organizations

There were items request and claim from other council and organizations. E.g. on 8 May 2013, there was a claim for 8 stacking chairs by Amanda Lough, School Business Manager of Ryhope Junior School.

Action taken:  Reply and claim cancellation with apology being unable to swap any item with outside NTC.

8.3 Member registration

One of the staff members from NTC tried to register in WARPit from main webpage and end  up with membership fee page.

Action taken: Asked him to visit NTC WARPit page (www.warp-it.co.uk/ntc) and register. Lesson learnt: Its better to share www.warp.it.co.uk/ntc in all communication.

8.4 Exactness of item:

When items are uploaded based on the inventory send by respective office staff, there was little confusion in the exactness of the item and also availability.

Action taken: Repeated communication with relevant photos and updated inventory list was been done. During 1st week of June, items from North Shield library were directly uploaded from Allan Wraight’s account. So this will avoid the earlier problems.

8.5 Different Date

Items uploaded with available date on 17 June were shown for 21st June in WARPit.

Action taken: Reported to WARPit administration

- Figures/ Key performance Indicators

The major key performance indicators since March 2013 to end of April are:

- £3,348 has been saved. The figure till February 2013 was £350 (approx)

- 1,746 kg of CO2 emission prevented

- 602 kg of waste diverted from being sent to landfill

- Recommendations/ Future direction

- As a lesson learnt both inventory listing and uploading in WARPit needs to be done by only one person, be it dedicated resource for WARPit or the respective staff from any service area (e.g. Whitley bay library).

- Also there should be image view options for items that are collected. Because without image of the collected item, it is confusing to find the exact item when there are variety of items under the same heading. Example under single heading ‘Storage’ there are kinder-boxes, drawers and more.

- For more inventories of items to be diverted, cooperate with "capital development teams" or equivalent as they will have a schedule of building/ school closures or re-furbishment.

Annex:

- (Annex-I: WARPit users’ report at NTC)

- WARPit news in ‘Teamwork’ newsletter, March issue

- Copy of letter send to schools

- WARPit news in 7 May – Team News

- WARPit news in ‘Team

- Screen shot of NTC WARPit page

Prepared by: Suman Dhun Shrestha

Contact: suman.shrestha@northtyneside.gov.uk, dhun.suman@gmail.com